## Sheet1
DFF- PROJECT PLAN/ESTIMATION
# | Milestones/Task | Estimation(In days) | Resource | Comments | StartDate | ENDDate
1 | Analysis of Source system/data
| Source System analysis | 3 | Prasad/Nitesh/Mitch |  | 2019-04-10 | 2019-07-10
| Extract the business rules from existing process | 3 | Anmol/Moulshree/Mitch |  | 2019-07-10 | 2019-10-10
| Data profiling | 2 | Nitesh/Anmol/Moulshree |  | 2019-07-10 | 2019-08-10
2 | Environment setup
| Creating the ODS* and STG database | 1 | Prasad/Nitesh | Statging Database completed | 26/09/2019 | 26/09/2019
| Setup the process to establish the connection between ODS and STG database | 1 | Prasad/Nitesh | Completed | 27/09/2019 | 27/09/2019
| Code Repository | 1 | Prasad/Nitesh/Mitch |  | 2019-09-10 | 2019-09-10
3 | Conceptual Model
| Identify the business entity, attributes | 3 | Prasad/Mitch/Nitesh |  | 2019-10-10 | 14/10/2019
| Identify and define the relationship | 2 | Prasad/Mitch/Nitesh |  | 14/10/2019 | 17/10/2019
4 | Logical Model
| Define Dimension | 3 | Prasad/Mitch/Nitesh |  | 18/10/2019 | 22/10/2019
| Define Facts | 3 | Prasad/Mitch/Nitesh |  | 23/10/2019 | 25/10/2019
| Design ERD for star schema/ snowflake schema | 2 | Prasad/Mitch/Nitesh |  | 30/10/2019 | 31/10/2019
| Create mapping document | 3 | Prasad/Mitch/Nitesh |  | 2019-01-11 | 2019-05-11
5 | ETL Design
| Create configuration and Audit tables | 2 | Moulshree/Anmol |  | 2019-06-11 | 2019-07-11
| Create procedure to load the confige/audit data | 3 | Moulshree/Anmol |  | 2019-08-11 | 2019-12-11
| Create procedure/script to audit the ETL process | 3 | Moulshree/Anmol |  | 13/11/2019 | 15/11/2019
6 | Build ODS tables
| Create ODS tables | 2 | Nitesh/Anmol/Moulshree | Required days may be vary depending on below factors: 1. complexity of the source data 2. Depending the number of ADF jobs and tables | 2019-06-11 | 2019-07-11
| Create ADF to load the ODS tables | 3 | Nitesh/Anmol/Moulshree |  | 2019-11-11 | 13/11/2019
| Unit testing and data validation with source | 1 | Nitesh/Anmol/Moulshree |  | 14/11/2019 | 15/11/219
7 | Build Stg tables
| Create staging tables | 2 | Nitesh/Anmol/Moulshree | Required days may be vary depending on below factors: 1. complexity of the business rule. 2. Depending the number of ADF jobs and tables | 2019-11-10 | 14/10/2019
| Create procedure to load the STG tables/implement Business Rules | 5 | Nitesh/Anmol/Moulshree |  | 14/10/2019 | 21/10/2019
| Prepare test cases to validate the Business Rules | 2 | Nitesh/Anmol/Moulshree
8 | Process Data into Model (Convert logical model to Physical )
| Create dimension, fact, xRef tables | 5 | Nitesh/Anmol/Moulshree |  | 2019-04-11 | 2019-08-11
| Define constraints on table (Primary Key, Foreign Key,Unique) | 3 | Nitesh/Anmol/Moulshree |  | 2019-11-11 | 14/11/2019
| Create stored procedures to process the data into data model | 5 | Nitesh/Anmol/Moulshree |  | 15/11/2019 | 22/11/2019
| Create process to implement the archival mechanism | 3 | Nitesh/Anmol/Moulshree |  | 25/11/2019 | 27/11/2019
9 | Integration Testing
| Integration testing on UAT environment | 3 | Team |  | 28/11/2019 | 30/11/2019
10 | Building SSAS cube
| Create SSAS cube/calculation etc | Timelines to be decided | Nitesh/Anmol/Moulshree | Depend above task completion we can decide the timeline for these below task
11 | Reporting
| Create Reports as per client requirement | Timelines to be decided | Mitch/Erik/Lance
12 | Production Deployment & Documentation
| Create design document, flow chart, mapping document and user manual* | 2 | Prasad
| Create deployment guide | 1 | Prasad
| Prepare scripts/code for deployment | 1 | Nitesh/Anmol/Moulshree
13 | Production Support
| Handover to production team | 1